Name:	Emmanuel Teye Adjei

Student ID: 2025/GCR/12765

Email: gcr2512765@students.icdfa.edu.ng

Word Count: 3,143

Business Continuity and Disaster Recovery Plan: Northbridge Skills Institute

Executive Summary

This document establishes the comprehensive Business Continuity (BC) and Disaster Recovery (DR) plan for Northbridge Skills Institute following the flooding and power failure incident at 08:00 WAT on Day 0. Serving as the Business Continuity and Disaster Recovery Coordinator, this report addresses all six required operational tasks: conducting a Business Impact Analysis (BIA), establishing recovery objectives and backup designs, evaluating strategy packages and budgets, formulating a coordinated BC/DR plan and runbook, scheduling recovery drills and managing table-top injects, and implementing governance, compliance and performance metrics.

Task 1: Business Impact Analysis (BIA) and Prioritization

1. Five-Function BIA Matrix

The Business Impact Analysis evaluates the operational disruption across Northbridge Skills Institute's five critical functions (F1 to F5), identifying owners, impacted stakeholders, dependencies and minimum service levels.

| Function | Owner Role | Users Affected | Critical Resources & Dependencies | Impact Over Time (0–24h) | Minimum Acceptable Service & Controls | Proposed Recovery Priority |
| --- | --- | --- | --- | --- | --- | --- |
| F1: Teaching & Assessment | Academic Director | 1,800 learners, 90 staff | LMS01, DB01, AUTH01, recovery network, centre workstations | High financial, severe reputation, exam disruption | Assessment platform available with offline/alternative submission; dual-signoff grading | Priority 1 (Critical) |
| F2: Fees & Finance | Chief Financial Officer | 1,800 learners, external payment provider | FIN01, DB01, AUTH01, external payment gateway | Cash flow interruption, reconciliation backlog | External gateway active; manual receipt logging with treasurer sign-off | Priority 2 |
| F3: Admissions & Registration | Registrar | Prospective learners, admissions staff | REG01, DB01, AUTH01, internet connectivity | Lost enrolment revenue, brand erosion | Provisional email registration queue; manual verification registry | Priority 3 |
| F4: Staff Payroll | HR Manager | 90 staff members | HR01, DB01, AUTH01, banking interface | Staff dissatisfaction, labour grievances | Verified payroll export files submitted by 12:00 Day 1 with dual-manager audit | Priority 4 |
| F5: Records & Certificates | Academic Registrar | Alumni, employers, administrative staff | FS01, AUTH01, secure file storage | SLA breach, verification delays | Manual file retrieval from encrypted backup image with audit logging | Priority 5 |

Table 1. Business Impact Analysis

2. Disruption Cost Calculations

Disruption costs are calculated for the first 8 hours and 24 hours using non-overlapping incremental disruption rates, incorporating the one-off examination rescheduling trigger for F1.

- F1 (Teaching & Assessment): Rate: NGN 60,000/hr. Exam scheduled at 11:00 WAT (3 hours post-disruption). Because assessment service is unavailable at 11:00, the NGN 120,000 rescheduling cost applies.

  - 8-Hour Cost: 8×NGN 60,000+NGN 120,000=NGN 480,000+NGN 120,000=NGN 600,000.

  - 24-Hour Cost: 24×NGN 60,000+NGN 120,000=NGN 1,440,000+NGN 120,000=NGN 1,560,000.

- F2 (Fees & Finance): Rate: NGN 40,000/hr. Fee confirmation deadline at 16:00 Day 0 (8 hours post-disruption).

  - 8-Hour Cost: 8×NGN 40,000=NGN 320,000.

  - 24-Hour Cost: 24×NGN 40,000=NGN 960,000.

- F3 (Admissions & Registration): Rate: NGN 20,000/hr. Admissions close at 18:00 Day 0 (10 hours post-disruption).

  - 8-Hour Cost: 8×NGN 20,000=NGN 160,000.

  - 24-Hour Cost: 24×NGN 20,000=NGN 480,000.

- F4 (Staff Payroll): Rate: NGN 10,000/hr. Bank submission deadline at 12:00 Day 1 (28 hours but accrues full 24 hours within the Day 0 baseline window).

  - 8-Hour Cost: 8×NGN 10,000=NGN 80,000.

  - 24-Hour Cost: 24×NGN 10,000=NGN 240,000.

- F5 (Records & Certificates): Rate: NGN 5,000/hr. 48-hour service commitment.

  - 8-Hour Cost: 8×NGN 5,000=NGN 40,000.

  - 24-Hour Cost: 24×NGN 5,000=NGN 120,000.

Combined Disruption Totals

- Total 8-Hour Disruption Cost: NGN 600,000+NGN 320,000+NGN 160,000+NGN 80,000+NGN 40,000=NGN 1,200,000.

- Total 24-Hour Disruption Cost: NGN 1,560,000+NGN 960,000+NGN 480,000+NGN 240,000+NGN 120,000=NGN 3,360,000.

3. Limitations and Qualitative Distinctions

- Estimation Limitations: These calculations represent exercise models and financial proxies rather than observed operational losses. They assume linear cost accumulation and do not capture compounding secondary effects such as regulatory penalties or long-term brand abandonment.

- Qualitative vs. Financial Impact: Financial impact measures direct monetary loss and transactional delay, whereas learner welfare involves academic progression, stress, and equity of access (e.g., 40 learners requiring centre workstations against a 25-workstation alternate facility limit). Reputation impacts institutional credibility, while data integrity ensures uncorrupted academic records and financial ledgers.

4. Dependency Risks and Technical Sequencing

- Business Priority vs. Technical Order: Business priority places teaching and assessment (F1) first due to the imminent 11:00 examination. However, technical restoration requires a strict bottom-up sequence: Recovery Network →AUTH01 (Local Directory) →Security/Backup Checks →DB01 (Central Database) before application-layer restoration (LMS01, FIN01, REG01, HR01, FS01) can occur.

- Critical Dependency Risks:

  - Shared Administrator Identity: Production and network backup administration share a single administrator identity, creating a single point of credential failure.

  - Local Directory Isolation: Local applications rely on AUTH01, which must be fully operational before database restoration can begin.

  - Resource Bottlenecks: Only 25 workstations are available at the alternate facility at 10:00, while 40 learners require centre workstations, creating a capacity deficit.

Task 2: Recovery Objectives and Backup Design

1. Definitions:

Recovery Time Objective (RTO) is the maximum acceptable time to restore a function to its minimum service level. Recovery Point Objective (RPO) is the maximum acceptable data loss measured backward from the disruption point. Maximum Tolerable Time (MTD) is the absolute business tolerance beyond which organisational viability is threatened; RTO must sit within MTD with a justified buffer.

2. Recovery Objectives Matrix

To govern restoration thresholds, numerical targets are established for Recovery Time Objective (RTO), Recovery Point Objective (RPO), and Maximum Tolerable Downtime (MTD), incorporating a safe operational buffer before business disruption limits are breached.

| Function | RTO Target | RPO Target | MTD Limit | Service Level for Declaration & Buffer |
| --- | --- | --- | --- | --- |
| F1: Teaching & Assessment | 3.5 Hours | 1 Hour | 6 Hours | LMS operational with active exam portal; 30-minute buffer prior to exam start |
| F2: Fees & Finance | 6 Hours | 1 Hour | 12 Hours | Gateway reconciliation active; 2-hour buffer before 16:00 deadline |
| F3: Admissions & Registration | 8 Hours | 4 Hours | 16 Hours | Registration portal open; 2-hour buffer before 18:00 closure |
| F4: Staff Payroll | 20 Hours | 12 Hours | 30 Hours | Payroll extraction verified; 4-hour buffer before 12:00 Day 1 submission. |
| F5: Records & Certificates | 24 Hours | 12 Hours | 48 Hours | FS01 file store mounted; 24-hour buffer within 48-hour SLA. |

Table 2. Recovery Objectives and Backup Design

3. Checkpoint Analysis and Data-Loss Windows

- Checkpoint Ages at 08:00 Disruption:

  - B01 (DB01 Full Backup): Taken at 23:00, Day minus 1 (9 hours old at 08:00 Day 0).

  - B02 (DB01 Incremental Chain): Taken at 07:00, Day 0 (1 hour old at 08:00 Day 0). Requires B01 and every incremental through 07:00.

  - B03 (AUTH01 Snapshot): Taken at 00:00, Day 0 (8 hours old at 08:00 Day 0).

  - B04 (FS01 Full Backup): Taken at 23:00, Day minus 1 (9 hours old at 08:00 Day 0).

  - Disconnected Full Backup: Taken at 17:00, Day minus 3.

- Reconciliation & Assumptions: Transactions executed between 07:00 and 08:00 on Day 0 cannot be assumed recoverable from database logs unless incremental transaction logs are successfully replayed. Temporary manual receipts and offline learner submissions must be reconciled against gateway transaction logs.

4. Backup and Restoration Design (3-2-1 Principle)

- Architecture: Adheres to the 3-2-1 backup principle (3 copies, 2 different media, 1 offsite immutable copy).

- Schedule: Daily incremental backups at 07:00 and 23:00; weekly full backups on Sundays at 23:00.

Security & Integrity: Offsite storage alone does not prove recoverability because encrypted backups may be corrupt, keys may be lost, or the restoration environment may lack compatible software. Access independence is currently undocumented: the offsite provider's controls must be audited to confirm that a compromised production admin cannot delete or encrypt offsite copies.

- Verification steps include:

- quarterly full-restore drills with business-data validation

- separate credential sets for backup storage and

- enforces AES-256 encryption in transit and at rest. Hash-chain integrity checks on every incremental.

Task 3: Recovery Strategy and Budget

1. Strategy Option Matrix

Three disaster recovery packages covering all five functions and shared infrastructure are evaluated against operational constraints.

| Package | Annual Base Cost (NGN) | Estimated First Critical Service | Data-Loss Window | Staffing & Geographic Fit |
| --- | --- | --- | --- | --- |
| Cold Site | 600,000 | 24 to 48 hours | Up to 24 hours | Requires extensive manual setup; fails F1 RTO |
| Warm Site | 1,500,000 | 3 to 5 hours | 1 to 6 hours | Fits staffing limits and alternate facility constraints |
| Hot Site | 2,400,000 | About 1 hour | Up to 15 minutes | Exceeds annual budget when additions are included |

Table 3. Recovery Strategy and Budget

2. Itemised Annual Budget

The annual planning limit is NGN 3,000,000. All packages require an additional NGN 400,000 annually for independent protected backups and NGN 200,000 for training and testing.

- Cold Site Total: NGN 600,000+NGN 400,000+NGN 200,000=NGN 1,200,000 (Within NGN 3M limit but fails RTO).

- Warm Site Total: NGN 1,500,000+NGN 400,000+NGN 200,000=NGN 2,100,000 (Recommended Option; within NGN 3M limit).

- Hot Site Total: NGN 2,400,000+NGN 400,000+NGN 200,000=NGN 3,000,000(Exactly at limit, leaving zero operational buffer for contingencies).

3. Recommendation, Trade-offs and ROI

- Selection: The Warm Site Package is recommended. It balances cost (NGN 2,100,000 total) with operational requirements, fitting comfortably within the NGN 3,000,000 annual ceiling.

- Trade-offs & Residual Risks: The Warm Site provides a first critical service window of 3 to 5 hours, meaning the 11:00 examination for F1 will experience a delay, incurring the NGN 120,000 rescheduling fee. Management accepts this residual risk.

- ROI Limitations: Single-outage estimates (e.g., the NGN 1,200,000 8-hour disruption cost) cannot alone establish annual ROI without factoring probabilistic risk exposure over time. Vendor recovery claims must be validated through rigorous pre-approval technical audits and SLA stress testing.

Task 4: Coordinated Continuity and Recovery Plan

1. Governance and Activation Framework

- Scope: Encompasses all 90 staff, 1,800 learners and digital infrastructure across primary and alternate facilities.

- Authorized Decision Maker: Business Continuity and Disaster Recovery Coordinator (Primary); Academic Director (Deputy).

- Activation Thresholds: Flooding, structural power failure exceeding 2 hours, or formal facilities declaration that the main site is inaccessible for ≥72 hours.

- Communication: Microsoft 365 email and mobile internet serve as primary out-of-band communication channels.

- Team Coordination: The continuity team (business coordinators) manages temporary services and learner welfare. The technical recovery team (2 technicians) executes the DR runbook. Facilities staff assess site safety. The incident response team activates only if the 30-minute inject (unexpected admin logon) indicates compromise.

Responsible Accountable Consulted Informed (RACI) Matrix

| Activity / Process | BC/DR Coordinator | IT Technical Team | Facilities Staff | Academic Director | Communications Lead |
| --- | --- | --- | --- | --- | --- |
| Plan Activation & Escalation | A / R | C | C | I | I |
| Temporary Assessment Delivery (F1) | A | C | R | R | I |
| Backup Validation & Integrity Checks | A | R / A | I | I | I |
| Infrastructure & Database Restoration | A | R / A | I | I | I |
| Stakeholder Communication & Notices | C | I | I | A | R |
| Return to Primary Site & Sign-off | A | R | R | C | I |

Table 4. Responsible Accountable Consulted Informed Matrix

3. Temporary Procedures (72-Hour Outage)

- F1: The 11:00 examination proceeds at the alternate facility using 25 workstations for 25 of the 40 centre-dependent learners; the remaining 15 use supervised BYOD with locked-down browser profiles. The 80 BYOD learners use their own devices. Paper scripts serve as fallback. Invigilators verify identity via photo ID and AUTH01 cached credentials. All scripts are sealed and logged for later digital upload.

Approval: Academic Registrar signs off on result validity.

- F2: Finance staff record fee confirmations manually against the external payment provider's real-time dashboard. A spreadsheet ledger captures learner ID, amount, timestamp and provider reference. Reconciliation against restored FIN01 occurs post-recovery.

Approval: Finance Manager countersigns daily.

- F3: Admissions intake shifts to email and phone. Applications are logged in a shared MS 365 spreadsheet with version history. No registration changes are committed until REG01 is restored.

Approval: Admissions Officer validates entries.

- F4: Payroll uses the last confirmed schedule (B01 full backup at 23:00 Day −1). HR submits instructions to the bank via the bank's web portal before the 12:00 Day 1 deadline. Any changes since the backup are deferred to the next cycle. Approval: HR Manager and Finance Manager dual-authorise.

- F5: Certificate requests are acknowledged by email with a revised 72-hour SLA. Urgent requests are fulfilled from locally cached PDFs where available.

Approval: Records Officer.

4. Disaster Recovery Runbook

- Step 1: Verify physical and network isolation of primary site; establish command post at alternate facility.

- Step 2: Execute Recovery Network setup

- Duration: 30 mins;

- Owner: Tech 1.

- Step 3: Restore AUTH01 local directory from snapshot B03

- Duration: 30 mins;

- Prerequisite: Network;

- Owner: Tech 1.

- Step 4: Perform Security and Backup Integrity Checks

- Duration: 30 mins;

- Prerequisite: AUTH01;

- Owner: Tech 1.

- Step 5: Restore DB01 using Full Backup B01 and Incremental Chain B02

- Duration: 90 mins;

  - Prerequisite: Security Checks;

  - Owner: Tech 2.

- Step 6: Restore application layers (LMS01, FIN01, REG01, HR01, FS01) in parallel/sequence.

- Step 7: Conduct business acceptance testing and sign-off; initiate controlled rollback if data corruption is detected.

5. Stakeholder Communication & Initial Learner Notice

Stakeholder matrix: Learners (SMS + Teams, every 6 h), Staff (Teams, every 2 h), Exam Board (email, at activation and resolution), Board Chair (phone, at 24 h), Payment Provider (email, at activation)

- Initial Learner Notice:

"Dear Northbridge Skills Institute Learners,

Due to unforeseen flooding and power failure at our main campus at 08:00 WAT today, our primary facilities are temporarily unavailable. Microsoft 365 email and communication channels remain fully active via mobile internet. Our 11:00 examination is being rescheduled to accommodate alternative arrangements. Eighty learners will utilize personal devices, and rotational access to our 25 alternate facility workstations will be provided starting at 10:00 WAT.

All online classes are suspended for today. Fee payments continue through the usual payment portal; retain your confirmation receipts. Admissions remain open via email to admissions@northbridge.edu.ng.

Further updates will be issued via your student email within the hour. We appreciate your patience as we ensure academic continuity."

- Incident Response Trigger: Unconfirmed system modifications, unauthorized privilege escalation, or data exfiltration indicators will immediately trigger formal Incident Response involvement alongside disaster recovery.

- Safe return: Facilities clearance (structural, electrical, environmental) → IT infrastructure validation → controlled data migration of temporary records → business-owner sign-off → phased learner return.

Task 5: Recovery Schedule and Exercise

1. Baseline Warm Site Schedule & Dependency Path

Operating with two technicians and respecting the strict prerequisite and parallelism rules, the deterministic schedule is established below:

| Action | Tech | Start | Finish | Prerequisite |
| --- | --- | --- | --- | --- |
| Recovery network | T1 | 08:00 | 08:30 | None |
| AUTH01 restoration | T1 | 08:30 | 09:00 | Network |
| Security & Backup checks | T1 | 09:00 | 09:30 | AUTH01 |
| DB01 restoration | T1 | 09:30 | 11:00 | Security checks |
| FS01 restoration | T2 | 09:30 | 10:30 | AUTH01 + Security |
| LMS01 restoration | T1 | 11:00 | 11:45 | DB01 |
| FIN01 restoration | T2 | 11:00 | 11:30 | DB01 |
| REG01 restoration | T2 | 11:30 | 12:00 | DB01 |
| HR01 restoration | T1 | 11:45 | 12:30 | DB01 |

Table 5. Warm Site Schedule and Dependency Path

Critical path to F1: Network → AUTH01 → Security → DB01 → LMS01 = 225 minutes (3 h 45 min). F1 available at 11:45, missing the 11:00 exam by 45 minutes. All functions recovered by 12:30.

Elapsed Recovery Times & Workarounds

- Earliest Assessment Service Restoration (LMS01): 11:45 WAT (Day 0). Because the examination starts at 11:00 WAT, LMS01 is not available on time, triggering the NGN 120,000 rescheduling fee.

- Feasible Completion Time for All Functions: 12:15 WAT (Day 0).

- Comparison: Modelled baseline results demonstrate that while technical recovery completes within 4.25 hours, business deadlines (such as the 11:00 exam) require pre-planned manual workarounds.

These are modelled baseline results, not a live test. F1 misses its RTO by 45 minutes and the exam deadline, confirming that the continuity workaround (manual/paper examination) is essential even when technical restoration succeeds.

2. Tabletop Exercise Log (45-Minute Stress Scenario)

| Exercise Time | Injected Event / Stress Factor | Decision & Revised Action | Owner & Rationale | Effect on Service / Recovery |
| --- | --- | --- | --- | --- |
| Minute 10 | Site closure extends from 72 hours to 5 days | Extend alternate facility lease agreement; transition staff to remote/hybrid schedules | Facilities Lead / Coordinator; ensures long-term operational viability | Extends operational continuity horizon beyond initial 3-day window |
| Minute 20 | Alternate facility capacity drops to 15 workstations | Enforce strict 3-tier rotational exam schedule; mandate BYOD for all 80 capable learners | Academic Director; mitigates physical bottleneck | Preserves exam integrity within reduced hardware constraints |
| Minute 30 | DB01 incremental backup fails integrity check; unexpected admin logon | Isolate backup server, fail back to B01 full backup (23:00 Day minus 1), audit admin credentials | IT Security Lead; addresses data corruption & security anomaly | Increases RPO gap by 8 hours; requires manual transaction reconciliation |
| Minute 40 | Payment provider reports successful payments absent from restored finance records | Activate manual payment ledger reconciliation using gateway API transaction logs. | Chief Financial Officer; ensures financial accuracy. | Prevents financial discrepancy; extends F2 reconciliation window. |

Table 6. Tabletop Exercise Log

Corrective Actions

| Action | Priority | Owner | Target Date | Evidence |
| --- | --- | --- | --- | --- |
| CA-01: Decouple production and backup administrator credentials | High | IT Security | Day 3 | IAM Role Separation Audit Report |
| CA-02: Implement automated cryptographic hash verification on all incremental backup chains | High | Senior DBA | Day 5 | Automated Checksum Script Logs |
| CA-03: Procure 25 mobile hot-spots and rugged loaner laptops for alternate site resilience | Medium | Procurement | Day 7 | Asset Inventory Sign-off |
| CA-04: Update student BYOD onboarding documentation for emergency remote examinations | Medium | Academic Registrar | Day 10 | Published Portal Policy |
| CA-05: Conduct bi-annual unannounced disaster recovery tabletop drills | High | BC/DR Coordinator | Quarterly | ; Exercise After-Action Report |

Table 7. Corrective Actions

Task 6: Governance and Performance Measures

1. Governance, Standards Alignment and Climate Considerations

- Plan Ownership & Approval: Owned by the Business Continuity and Disaster Recovery Coordinator; formally approved by the Chief Executive Officer and Governing Council.

- Framework Alignment:

  - NIST SP 800-34 Revision 1: Mapped to Contingency Planning Policy, Business Impact Analysis, Preventive Controls and Continuity Operations.

  - ISO 22301:2019 (including Amendment 1:2024 Climate Action changes): Mapped to Context of the Organization, Leadership, Business Continuity Planning, and Performance Evaluation.

- Climate Consideration (ISO 22301 Amendment 1:2024): The primary site flooding incident highlights physical climate vulnerability. Climate risk assessments are integrated into site selection, mandating raised electrical infrastructure and flood-barrier resilience for all future capital developments.

2. Key Performance Indicators (KPIs) Dashboard

| Metric Name | Formula / Measurement Method | Data Source | Target | Reporting Frequency | Accountable Owner |
| --- | --- | --- | --- | --- | --- |
| Recovery Performance (RTO Compliance) | ("Actual Restoration Time" ≤"Target RTO" )×100% | DR Incident Logs | ≥95% compliance | Per Exercise / Incident | BC/DR Coordinator |
| Restoration-Test Coverage | ("Successfully Tested Datasets" ÷"Total Critical Datasets”) ×100% | Backup Audit Logs | 100% semi-annually | Bi-annually | Senior DBA |
| Corrective-Action Closure Rate | ("Closed Corrective Actions" ÷"Identified Actions" )×100% | Audit Management System | ≥90% within 30 days | Monthly | Compliance Officer |
| Staff Training Completion | ("Staff Trained in BC/DR Roles" ÷"Total Staff 90" )×100% | LMS HR Module | 100% annually | Annually | HR Manager |

Table 8. Key Performance Indicators Dashboard

3. Maturity Assessment & 12-Month Improvement Target

- Current Maturity Level: Level 2 (Managed / Reactive) under standard BC maturity models. Plans exist on paper, but dependency on shared admin credentials, manual reconciliation workarounds, and unverified backup chains indicate vulnerability.

- 12-Month Target: Level 4 (Proactively Managed / Resilient). Achieving this target requires automating backup integrity checks, decoupling administrative identities, securing secondary workstation redundancy, and institutionalizing quarterly simulation exercises.

References

- ICDFA. Business Continuity and Disaster Recovery. GRC205, Week 21

- NIST (2010, updated November 2010). SP 800-34 Revision 1. Contingency Planning Guide for Federal Information Systems. Official guide and BIA templates.

- ISO. ISO 22301:2019. Business continuity management systems. Official overview and preview.

- ISO. ISO 22301:2019 Amendment 1:2024. Climate action changes. Official amendment page.